## Schedule
S.No | Description | Module | Deployment Date | Assigned to
1 | The following information has to be saved in Capital letters irrespective of any case is entered | Vendor Registration | 2016-05-21 | M
Vendor Name
PAN
CITY
VAT
CST
BANK NAME
IFSC
EXCISE
SERVICE TAX
Muncipal Corporation Name
MSME
2 | PAN Number text from small to caps is not happening |  |  | M
3 | ECC Number - Validation not working validation is not working properly |  |  | M
4 | MSME number is 12 alpha number and if yes document has to be uploaded |  |  | M
5 | 5th letter validation of PAN card is Company's first letter its not working properly |  |  | M
6 | The comment on the address "Your "correspondence" address (We shall send purchase orders, cheques for payments etc to this address)" has to be in the bigger font | Vendor Registration |  | M
7 | a. under the General Information tab, the Address 2 & Address 3 fields, if the address is same as correspondence address then please provide a “same as above” button to copy the address. |  |  | M
8 | Address 1 and Address 2 Field has to be long to fit in the row. An astrick to indicate that Address1, Address2, City, State, Pin and country is mandatory. Address 3 can be removed |  |  | M
9 | First address the PIN/ZIP validation is done for 6 numbers but for other address it is not working. |  |  | M
12 | Password validation criteria- 8 to 18 letters minimum, one Capital one small and one numeric | Application |  | N
13 | Bank account number to be retyped in the second attempt as a separate information. First typed information will be starred. If there is difference in both the entries it should be errored | Vendor Registration |  | N
14 | On the first page wherein Vendor / Employee enter their credentials (Login ID & Pwd) there must be information about the minimum screen display dimensions and minimum browser requirements. | Application |  | N
15 | Sequence of all comments should be such that the latest comment should be the topmost appearing comment with prior comments appearing below. | Proposer Section |  | N
| All comments should have Date and Timestamp. Datestamp was available but Timestamp was not observed in the demo run and this needs to be fixed. |  |  | N
16 | Session out time to fixed as 5 mins | Application |  | N
17 | Error Message color is very bright red can it be softer in Red Colour | Application |  | N
23 | Search By Vendor Code/ PAN NUM | Proposer |  | T
24 | Assigning QAC/FA across division by Admin | Admin |  | T
25 | Forgot Password | Application |  | T
27 | LDAP directory to authenticate / validate Thermax employees upon login through active directory. | Application | 2016-05-23 | Y
28 | SMTP server settings. | Application |  | Y
10 | Key Contacts saving cross check in database | Vendor Registration | 2016-05-28 | M
11 | Item Category and Sub Category is not coming for selection add Item category and Sub category master (Max 10 lines for multiple categories) | Vendor Registration |  | M
26 | Status Updates | Vendor Registration |  | M
34 | On Submit the system should next page should open. On click of each save the next tab will open. | Vendor Registration |  | M
35 | No Tab sequence is set or it is not working properly. | Vendor Registration |  | M
18 | 4 level approval process as below: (Proposer -> QAC -> Finance (Currently to be disabled) -> Final Approver -> Vendor Registration Cell (VRC) | Proposer/Approver |  | N
19 | Proposer should be provided a field / space to upload "Vendor Assessment report'. This should be "YES by default' with mandatory uploading of the assessment report. Only pdf file format to be allowed for uploading. If the proposer does not go with the "Yes (default)” option and instead selects "No' then comments are mandatory for the proposer to mention why vendor assessment report is not uploaded by him. (proposer section screen field) This is yet to be incorporated in the proposers section before he submits and puts it into approval workflow. | Proposer/Approver |  | N
20 | Proposer to be provided textbox for entering his “recommendation” along with document upload facility for “internal signed file note”. This is yet to be incorporated in the proposers section. | Proposer/Approver |  | N
21 | Proposer’s selection of “QAC” and “Final Approver” from a master list is pending. | Proposer/Approver |  | N
22 | Interdivision activation by proposer - demonstration is pending | Proposer/Approver |  | N
29 | ERP vendor master tables for synchronisation with Vendor Connect. | Application |  | Y
31 | Approval Process for Details Update | Vendor Registration |  | T
32 | Transferring Application to new Proposer | Admin |  | T
30 | Existing vendor data migration and updation on to Vendor Connect - demonstration is pending. | Application | 2016-06-03 | Y
33 | Add new site for existing vendor – demonstration is pending. | Proposer |  | N
36 | User Guide | Application |  | N
37 | FAQ | Application |  | N
38 | Database Dump | Application |  | N

## Points Not Clear
1 | 1. Check Box "I agree has to be checked and once checked it has to be disabled. 2. On Submit the the system should check that along with the Check Box the document is uploaded into the system | M
The download document should be a PDF (3 page ) attached to the website and could be downloaded on press of the download button
On the first time entry the CoC will be displayed and the Vendor will accept the accept check box. Once he uploads the document then accepted check box should remain in accepted condition and disabled for the changes
2. There has to be a note in the page before the "I Agree" check box. "on acceptance o" 3. Once the CoC is uploaded in the system we should have a message that "The Code of Conduct is accepted and uploaded"
2 | On selection of the Vendor Type the Statutory data list changes but once saved currently the Vendor Type cannot be changed. We have to allow the change in the Vendor Type and the change in the Vendor Type can clear all the previous data. | M
3 | A note to be added on the Vendor Name - ""
4 | Are there any legal cases pending against the company default option is yes currently its no, Template of the info can be copied from the TAB Management with "Name of Director and Partner working with Thermax" | M
5 | Bank information which are not filled has to be edited
6 | Unlocking and activating an inactive vendor code by proposer – demonstration is pending.
7 | Vendor data filling by Thermax employee (Bypass route) - demonstration is pending
8 | All titles to be formatted as Bold text.
9 | Reports